## Scenarios P0 (hidden)
Serial Nu | Test Scenarios | Pass/Fail | Test Comments | Pending Items
1 | >> LED device onboarding.
LED device must be on boarding sucessfull from dashboard as well as room level
User should be able to onboard the light to MirAIe using Android and IOS mobile app
User should be able to turn ON/OFF the lights remotely with Mobile app, virtual assistants and with physical switches ON/OFF
2 | >> Device Details page.
User must enter device details screen when clicks on dashboard widget and user must see below available option in details page. a. Switch ON/OFF toggle button b. Online/Offline status c. Temperature icon d. Colour wheel picker with combination of colors e. Gradient Picker with color value f. RGB Colour value button g. Brightness adjustment 0 to 100
3 | >> Click on RGB value button.
User must enter RGB color value details page when clicks on RGB value button and must see below available option in RGB details page. a. Switch ON/OFF toggle button b. Color light bulb d. Red colour light adjustment e. Green colour light adjustment f. Blue colour light adjustment g. Brightness adjustment 0 to 100 h. X button to close page and navigate back to device details page
4 | >>LED Light with Color Temperature and Brightness control.
User must enter to temperature and brightness control page when clicks on Temperature option and must see below available option in temperature and brightness control page a. Switch ON/OFF toggle button b. Temperature picker Warm and Cool c. Brightness adjustment 0 to 100 d. Shown alert message for color choosen here will overwright the previously chosen RGB colours e. Clicks on color selector image to navigate back to device details page
5 | >>Individual Device setting page.
User must enter to individual Light Setting page when clicks on 3 dot on right hand top side and must see below available option in setting page. A. LED light name b. Brand name c. Model details
6 | >>Advanced settings on device details page.
a. User should be able to configure the Rise Time of the light which will be used while turning on the light. Configuration should be in the range of 1 to 3 seconds in increments of 0.5 seconds. b. User should be able to configure the Fade Time of the light which will be used while turning off the light. Configuration should be in the range of 1 to 3 seconds in increments of 0.5 seconds. c. Users should be able to revert to the default power-on settings of the light d. Gamma Correction - User should be able to do Gamma correction in the range of 1 to 2.5 with a step value of 0.5. e. User can control the saturation between 0 and 100% by increasing the brightness of natural day light.
7 | >>One tap ON/OFF all lights on Room level details page
a. User must turn ON all lights clicking on Led lights button in room level details page b. User must turn OFF all lights clicking on Led lights button in room level details page
8 | >>Dashboard widget device details
User should see below details on dashboard widget a. Device name b. Online/Offline status c. Brightness image and value d. ON/OFF toggle button e. Light colour image

## App tour -Test Cases
Sr. No. | Test Scenarios | Steps | Test Case | Completion Date | Android | IOS | Dependency | Remarks | UI Screens | Developer Comments | Android Pass/Fail
1 | 1. New App Launch 2. User uninstalls the app and Reinstall on the same device 3. Clear data / Cache from OS settings | App launch > App loading screen | 1. App loading screen with MirAIe logo with Connected living text. |  |  |  |  | Loading Screen image after app launch Pixel phones will show 2 screens |  |  | Pass
2 |  | User onboarding screen 1 | Connected Devices Connect all your compatible smart devices with the MirAIe App. (With Graphics image) |  |  |  |  | a. Scrolling screen to right will show scren 2 b. With 1 of 3 highlighted dots |  |  | Pass
3 |  | User onboarding screen 2 | Control Appliances Control your devices on the go from the MirAIe App. (With Graphics image) |  |  |  |  | a. Scrolling screen 2 from left side will show screen 1 b. Scrolling screen 2 from right side with move to screen 3 c. With 2 of 3 highlighted dots |  |  | Pass
4 |  | User onboarding screen 3 | Sit back and relax Automate controls, quickly raise service requests and live the MirAIe life. Get Started button (With Graphics image) |  |  |  |  | a. Scrolling screen 3 from left side will show screen 2 b. With 3 of 3 highlighted dots |  |  | Pass
5 | Login / Sign up screen after user clicks on Get started button | User can able to see Login/Sign up and Forgot password? Details on the screen | User will land to Login/Sign up screen after App tour ends |  |  |  |  | Normal journey will continue for Login / Sign up |  |  | Pass
6 | First time user sign up journey | Click on Sign up > Enter mobile / email and registered | User will land to setup Home details page after successfully completed sign up for new user |  |  |  |  | In previous implement user land to App tour journey after new register successful |  |  | Pass
7 | From the App Setting Screen | App launch > User Login > Go to app settings screen > Click on Welcome To MirAIe option | User able to click on Welcome to MirAIe option from app setting screen | [7 empty] | Pass
8 |  | App launch > User Login > Go to app settings screen > Click on Welcome To MirAIe option > App Tour - Slide 1 | a. Connected Devices Connect all your compatible smart devices with the MirAIe App. b. Navigate back to app setting screen if user clicks on Back button on the top left hand corner. (With Graphics image) |  |  |  |  | a. Scrolling screen to right will show scren 2 b. With 1 of 3 highlighted dots |  |  | Pass
9 |  | App launch > User Login > Go to app settings screen > Click on Welcome To MirAIe option > App Tour - Slide 2 | a. Control Appliances Control your devices on the go from the MirAIe App. b. Navigate back to app setting screen if user clicks on Back button on the top left hand corner. (With Graphics image) |  |  |  |  | a. Scrolling screen 2 from left side will show screen 1 b. Scrolling screen 2 from right side with move to screen 3 c. With 2 of 3 highlighted dots |  |  | Pass
10 |  | App launch > User Login > Go to app settings screen > Click on Welcome To MirAIe option > App Tour - Slide 3 | a. Sit back and relax Automate controls, quickly raise service requests and live the MirAIe life. b. Navigate back to app setting screen after user move screen to right. c. Navigate back to app setting screen if user clicks on Back button on the top left hand corner. (With Graphics image) |  |  |  |  | a. Scrolling screen 3 from left side will show screen 2 b. With 3 of 3 highlighted dots |  |  | Pass
11 |  | App launch > User Login > Go to app settings screen > Click on Welcome To MirAIe option > App Tour ends > Click on back button | Navigate back to app setting screen after App Tour ends screen by clicking on back button |  |  |  |  | Clicks back button user will land to App setting screen | UI Team need to provide Done or close option |  | Pass
12 | Kill the app in between app tour after app launch. | App launch > App tour slides | Only after the screens are completely shown, it will be remembered and not shown again in the next launch. If user has not seen them completely, it has to show up again |  |  |  |  | The goal is user should see it atleast once completely |  |  | Pass

## Android Bugs
Sl. No | Steps | Issue summary | Priority | Status | Tested ver. / App center ver. | Resut Pass/Fail | Remarks | Responsibility | Developer comments
1 | User onboarding screen 3 | Below text is coming in 3 lines Automate controls, quickly raise service requests and live the MirAIe life. | Low | New | 1.3.30 | Pass |  | Dev teams | Fixed
2 | App launch > User Login > Go to app settings screen > Click on Welcome To MirAIe option | App Tour text need to be updated as per new changes mentioned below. Welcome to MirAIe instead App Tour | Low | New | 1.3.30 | Pass |  | Dev teams | Fixed
3 | App launch > User Login > Go to app settings screen > Click on Welcome To MirAIe option > App Tour - Slide 3 | Below text is coming in 3 lines Automate controls, quickly raise service requests and live the MirAIe life. | Low | New | 1.3.30 | Pass |  | Dev teams | Fixed
4 | User onboarding screen 1 | Device Blue color indicator is not placed on the device properly as per the figma design (UI issue) | Low | New | 1.3.30 | Fail |  | UI / UX | pending
5 | App launch > User Login > Go to app settings screen > Click on Welcome To MirAIe option > App Tour - Slide 1 | Device Blue color indicator is not placed on the device properly as per the figma design (UI issue) | Low | New | 1.3.30 | Fail |  | UI / UX | pending
6 | Click on Sign up > Enter mobile / email and registered | App is getting closed after user registered successfully, with out landing to add device onboarding journey. | High | New | 1.3.30 | Pass |  | Dev teams | Fixed
7 | Kill the app in between app tour after app launch. | App tour is not showing again If user has not seen them completely after killed app and re launch it again. | High | New | 1.3.30 | Pass |  | Dev teams | Fixed
8 | For All available slides on app launch app tour and app tour from app setting screen | Highlighted dot should be shown as per the UI screen | Low | New | 1.3.30 | Pass |  | Dev teams | Fixed
9 | Click on Sign up > Enter User name, Mobile number field and New passwrod field | New Password entry field is not visible to see the entering password, It is hiding from the keypad. | Medium | New | 1.3.30 | Pass |  | Dev teams | Fixed
10 | Click on Sign up > Enter mobile / email and registered > Home | Getting home creation failed message after successfully created account | Medium | New | 1.3.30 | Pass |  | Dev teams | Fixed

## Translation status
Serial Nu | Target screen | English | Hindi | Pass/Fail | Tamil | Pass/Fail | Marathi | Pass/Fail | Bengali | Pass/Fail | Telugu | Pass/Fail | Thai | Pass/Fail | Test Comments
1 | First Launch / settings | Connect Devices | उपकरणों को कनेक्ट करें | Pass | சாதனங்களை இணைக்கவும் | Pass | उपकरणे कनेक्ट करा | Pass | উপকরণগুলি সংযুক্ত করুন | Pass | పరికరాలను కనెక్ట్ చేయండి | Pass | เชื่อมต่ออุปกรณ์ | Pass
2 | First Launch / settings | Connect all your compatible smart devices with the MirAIe App. | अपने सभी अनुकूल स्मार्ट उपकरणों को MirAIe ऐप के साथ कनेक्ट करें | Pass | உங்கள் அனைத்து பொருட்களையும் MirAIe ஆப்புடன் இணைக்கவும் | Pass | आपल्या सर्व संगणकीय उपकरणांचे MirAIe अ‍ॅपशी संपर्क साधा | Pass | সমস্ত সাজানো স্মার্ট ডিভাইসগুলিকে MirAIe অ্যাপের সাথে সংযুক্ত করুন | Pass | మీ అన్ని అనుకూల స్మార్ట్ పరికరాలను MirAIe యాప్‌తో కనెక్ట్ చేయండి | Pass | เชื่อมต่ออุปกรณ์สมาร์ทที่เข้ากันได้ทั้งหมดของคุณกับแอปพลิเคชัน MirAIe | Pass
3 | First Launch / settings | Control Appliances | उपकरणों को नियंत्रित करें | Pass | மின்னணுக்களை கட்டுப்பாடு செய்யவும் | Pass | उपकरणांचे नियंत्रण करा | Pass | প্রয়োজনীয় উপকরণগুলি নিয়ন্ত্রণ করুন | Pass | పరికరాలను నియంత్రించండి | Pass | ควบคุมเครื่องใช้ไฟฟ้า | Pass
4 | First Launch / settings | Control your devices on the go from the MirAIe App. | MirAIe ऐप से कहीं से भी अपने उपकरणों को नियंत्रित करें | Pass | MirAIe ஆப் மூலம் எங்கிருந்தும் உங்கள் சாதனங்களைக் கட்டுப்படுத்தவும் | Pass | MirAIe अॅपसह कोठूनही तुमची डिव्हाइस नियंत्रित करा | Pass | MirAIe অ্যাপের মাধ্যমে যেকোনো জায়গা থেকে আপনার ডিভাইস নিয়ন্ত্রণ করুন | Pass | MirAIe యాప్‌తో ఎక్కడి నుండైనా మీ పరికరాలను నియంత్రించండి | Pass | ควบคุมอุปกรณ์ของคุณได้ทุกที่จากแอป MirAIe | Pass
5 |  | Sit back and relax | अब आप आराम से बैठिए | Pass | இப்போது ரிலாக்ஸ் செய்யவும் | Pass | आता आरामात बसा | Pass | এখন আরামে বসুন | Pass | ఇప్పుడు ఆరాంభం చేసుకోండి | Pass | นั่งพักผ่อนสบายๆ | Pass
6 |  | Automate controls, quickly raise service requests and live the MirAIe life. | नियंत्रण को स्वचालित करें, जल्दी से सेवा अनुरोध करें और MirAIe जीवन जिएं | Pass | கட்டுப்பாடுகளைத் தானியங்குபடுத்துங்கள், சேவைக் கோரிக்கைகளை விரைவாகச் செய்து, மிராயி வாழ்க்கையை வாழுங்கள் | Pass | नियंत्रणे स्वयंचलित करा, त्वरीत सेवा विनंत्या करा आणि MirAIe जीवन जगा. | Pass | স্বয়ংক্রিয় নিয়ন্ত্রণ, দ্রুত পরিষেবা অনুরোধ করুন এবং MirAIe জীবন যাপন করুন | Pass | నియంత్రణలను ఆటోమేట్ చేయండి, సర్వీస్ రిక్వెస్ట్‌లను త్వరగా చేయండి మరియు మిరాఐ జీవితాన్ని గడపండి | Pass | ควบคุมอัตโนมัติ เพิ่มคำขอบริการอย่างรวดเร็ว และใช้ชีวิตแบบ MirAIe | Pass
7 |  | Get Started | शुरू करें | NA | தொடங்கவும் | NA | सुरुवात करा | NA | শুরু করুন | NA | ప్రారంభించండి | NA | เริ่มต้น | NA
8 | Setting Page | Welcome to MirAIe | MirAIe में आपका स्वागत है | Pass | MirAIe-க்கு வரவேற்பு | Pass | MirAIe मध्ये आपले स्वागत आहे | Pass | MirAIe এ আপনাকে স্বাগতম | Pass | MirAIeకు స్వాగతం | Pass | ยินดีต้อนรับสู่ MirAIe | Pass