## Dashboard
AC , TV , STB, Learning+STB Channel
Category +Features | Bugs Reported
AC +Common Journey | 86
TV | 9
STB | 5
Learning+STB Channel | 43
Responsibility | Bugs Closed
Development Team | 126
UI/UX Team | 5
Firmware team | 4
Cloud Team | 8

## AC+Common Journey
Sr No | Issue Description | Priority | Status | Result | AppCenter Version | Remarks | Responsibility | Dev Status | Dev Comments
1 | Onboarding successful device name "IR Blaster ODMIRB" . It must be " IR Remote" | Medium | Closed | Pass | 717 |  | Cloud Team
2 | After remove added AC Remote .IR Remote Widget showing device icon and name on Widget . It is not reseting untill kill the app and launch | High | Closed | Pass | 711 |  | Development Team
3 | Contents on Widget need to aligned as per Figma Design . We must need to adjust Gap between Room and Tap to add Remote Room image and Room Name must need to aligned as per Figma Design | High | Closed | Pass | 711 |  | Development Team
4 | Add Remote Sequence must be AC , Television and STB after click on Plus Button in IR remote Details page | Medium | Closed | Pass | 711 |  | Development Team
5 | Gap between AC , Television and STB icons must be uniform and separated by vertical lines | High | Closed | Pass | 711 |  | Development Team
6 | Need to redesign text contents because it is showing Room Name .. | High | Closed | Pass | 711 |  | Development Team
7 | Add Remote Bottom Sheet should be Curve at top left and right side as per Figma Design | Medium | Closed | Pass | 711 |  | Development Team
8 | Select Brand and Model Bottom sheet should be Curve at top left and right side as per Figma Design | Medium | Closed | Pass | 711 |  | Development Team
9 | On Select AC remote page instruction "Tap on each key to test this remote . if the keys work , Select Remote, else explore other remotes" are not coming | Medium | Closed | Pass | 711 |  | Development Team
10 | In Save Remote Botton sheet need to aligned on Bottom side as per Figma Design | Medium | Closed | Pass | 711 |  | Development Team
11 | Save Remote allowing to enter text in second line | Medium | Closed | Pass | 711 |  | Development Team
12 | Save Remote Text Save button enable after enter minimum 10 characters - It should be min 2 | High | Closed | Pass | 707 |  | Development Team
13 | In Save Remote keyboard not dismiss if you touch outside of Save Remote Bottom Sheet - Please Check Rename Device Scenario | High | Closed | Pass | 723 |  | Development Team | Fixed
14 | After Save Remote .. Saving remote loader page not available | Medium | Closed | Pass | 711 |  | Development Team
15 | Snackbar message for Sucessfully added AC Remote missing like " AC Remote Successfully Added" | Medium | Closed | Pass | 711 |  | Development Team
16 | Controls are not working like Power ON/OFF, AC Mode , FAN Speed and Swings in Explorer Remote | High | Closed | Pass | 711 |  | Development Team
17 | Snack bar message for Successfully removed AC Remote missing like " My IR AC Remote Successfully Removed" | Medium | Closed | Pass | 711 |  | Development Team
18 | In IR settings page Device name by default should come as "IR Remote" instead of "IR BlasterODMIRB" | Medium | Closed | Pass | 717 |  | Cloud Team
19 | Keypad screen is not closing after coming back from Edit device Name in setting page. | High | Closed | Pass | 717 |  | Development Team
20 | For Search Model and Brand .. We can take reference of Blaze where they are showing Popular Brand list on first page and give option to search other brands .. It will improve user experience | High | Closed | Pass | 717 |  | UI/UX Team
21 | There's no exit pop up while coming back from adding remote page | Medium | Closed | Pass | 711 |  | Development Team
22 | While adding the AC remote, There's no message is showing that "Tap on each key to test this remote…." | Medium | Closed | Pass | 711 |  | Development Team
23 | In Explore remote or save remote page, AC temperature is not showing in the UI | Medium | Closed | Pass | 711 |  | Development Team
24 | Vertical swing is not showing, Only horizontal swing is showing in UI | Medium | Closed | Pass | 707 | Accepted | Development Team
25 | After saving the remote, "change remote" option is not available in AC remote details page | High | Closed | Pass | 717 |  | Development Team | Not Implementing
26 | After saving the remote, "+" icon is not showing in the bottom side of the AC details page | High | Closed | Pass | 711 |  | Development Team | Not Implementing
27 | There's no indication for ON/OFF button. | High | Closed | Pass | 711 |  | Development Team
28 | Click on mode cahange, AC is getting on but no change in the mode in Explorer Remote Journey | High | Closed | Pass | 707 |  | Development Team
29 | After clicking on start exploring, Select AC remote page shows bottom sheet for selection of brand and model. Expected to show page with disabled remote image and select AC remote on title bar. | High | Closed | Pass | 711 |  | Development Team
30 | After clicking on Rename Remote option, bottom sheet overlaped. User not able to see rename and cancel options | High | Closed | Pass | 717 |  | Development Team
31 | After remove AC remote, user must need to land IR remote details page. Currently after remove ac remote, user land but bottom sheet for add remote is opening | Medium | Closed | Pass | 711 |  | Development Team
32 | Brand name is not showing in IR Remote Settings page | Medium | Closed | Pass | 707 |  | Development Team
33 | UI is showing "ON" text for swing controls for both ON and OFF states | Medium | Closed | Pass | 711 |  | Development Team
34 | Fan speed and Swing text is not aligned properly as per the icon in explore journey for low, auto and high | High | Closed | Pass | 711 |  | Development Team
35 | In ofline state toast message is not popping up | Medium | Closed | Pass | 719 |  | Development Team
36 | Rename IR Remote Name from Setting > It is not updating on IR Remote details page | High | Closed | Pass | 711 |  | Development Team
37 | Click on Setting Button > User in IR Remote Setting Page > Press Back Arrow on Title bar > Add Remote Bottom Sheet [Expected user should land details page] | Medium | Closed | Pass | 711 |  | Development Team
38 | Device Diagnose for IR Remote showing wrong insruction and It is showing Anchor Fan journey | High | Closed | Pass | 711 | Need to rearrange instructions | Development Team
39 | in Explorer Remote Journey , Product images are missing | High | Closed | Pass | 711 |  | Development Team
40 | Select AC Brand and Model Drop down list not able to populate list a. Click on AC Brand > Brand list not populpate if user dismiss bottom sheet and come back b. Select AC Brand > Select Model > Model drop down list not populate c. Search Bar allowing only characters and not numbers d. Keypad also showing Right Mark but unable to dismiss Keypad c. if user select any wrong model then confirm button should not enable . Confirm button should enable only in case correct model and brand details are enter | High | Closed | Pass | 719 |  | Development Team
41 | Save Remote bottom sheet not going up after Keypad up and Save Remote button is not visible | High | Closed | Pass | 717 |  | Development Team
42 | App crashed and shows FATAL Exceptions [Session Cache] | High | Closed | Pass | 719 | Please refer logs for reference | Development Team
43 | Save Remote > Enter 2 Character> Keypad prompt option for type it in next line> Please show Right button , Click on Right Arrow , Keypad should dismiss>User should be in Save Remote Bottom sheet | Medium | Closed | Pass | 717 |  | Development Team
44 | App crashed for click on Explorer Button | High | Closed | Pass | 717 | Please refer logs for reference | Development Team
45 | User in Cool Mode > if he change temperature below or above 25 > then next mode not able to change > It shows cool and heat mode [If supported] and Auto /Dry mode is unavailable | High | Closed | Pass | 719 |  | Development Team
46 | Onboarding instruction need to aligned as per Zeplin and Title bar is missing . It must need to show "Setup Device" on Title Bar | High | Closed | Pass | 717 |  | Development Team
47 | Enter your WiFI Credentials Page showing AC Image instead of IR Remote | Medium | Closed | Pass | 717 |  | Development Team
48 | Rename Remote a. Edit curser should come at the end of Text b. User should not allow move next line c. Rename button should not enable untill user enter minimum 2 Character d. Min 2 and Max 20 Character should allow to enter e. No numericals and special characters allow to enter | High | Closed | Pass | 717 |  | Development Team
49 | Precondition : IR Remote having AC Remote > Offboard Main IR Remote >Onboard IR Remote again> Actual Result : Associated Remote also getting added , user trying to remove that Remote its always fails | High | Closed | Pass | 719 |  | UI/UX Team
50 | Intermediate issue for Showing AC Temperature . Temperature showing in one digit | High | Closed | Pass | 711 |  | Development Team
51 | Change WiFi Password instruction need to aligned as per Zeplin and Title bar is missing . It must need to show "Change Password" on Title Bar | Medium | Closed | Pass | 717 |  | Development Team
52 | Diagnose instruction need to alinged as per Zeplin and Title Bar is missing . It must need to show "Diagnose Device" on Title Bar | Medium | Closed | Pass | 717 |  | Development Team
53 | IR Remote Setting>Diagnose Device > Need to click 3 to 4 Times > then Device Diagnose instruction open | High | Closed | Pass | 717 |  | Development Team
54 | First change cool mode > change temperature to less than or greater than 25 > back to IR Remote details page > Then IR remote page status has been change for all parameter which is set before move to IR Remote Details page Eg. a. User set Cool Mode and Change Temperature to 17 Degree b. User move to IR Remote Details Page c. Again click on Remote and Enter save remote screen d. Here User will see mode , fan speed , Swing and temperature also changed | High | Closed | Pass | 717 |  | Development Team
55 | on Saved Remote page , Swing OFF text is not visible , We must need to make it more visible | Medium | Closed | Pass | 717 |  | Development Team
56 | App crashed after pull to refresh on Home . Observed 3 type crash .. Logs has been shared | High | Closed | Pass | 717 | Please refer logs for reference | Development Team
57 | App crashed after pull to refresh on Home , Home not loading | High | Closed | Pass | 717 | Please refer logs for reference | Development Team
58 | Latest Firmware with integrated library [Hardware would be support without Decoder ] | High | Closed | Pass | 1.05 |  | Firmware Team
59 | Final Hardware would be without Decoder | High | Closed | Pass | 1.05 |  | Firmware Team
60 | App crashed [User on Details page > Click on Plus Button > Select AC>Start Exploring> Select Brand] | High | Closed | Pass | 719 |  | Development Team
61 | User on Details page > Click on Plus Button > Select AC>Start Exploring> Select Brand>Select Model > Press Back Buton … After press Back Button Only Brand Search Box are visible | High | Closed | Pass | 719 |  | Development Team
62 | Onboarded IR Remote Device from Room . It is not showing in Room | High | Closed | Pass | 719 |  | Development Team
63 | Please do not show Auto Update and Update Manually options for iR remote on Setting Page .. Both are not relevant for IR remote for now | Medium | Closed | Pass | 719 |  | Development Team
64 | AC Models are showing double in list | High | Closed | Pass | 726 |  | Cloud Team
65 | Please remove Blaster from Explore Page of "Ensure No Obstructions". It must be Remote instead of Blaster | Low | Closed | Pass | 719 |  | Development Team
66 | On Select AC Brand and Model , Text Box should show " Please select the brand" or "Please select any model" Instead of " Please enter the brand name" "Please enter the brand name" showing wrong for select model | Medium | Closed | Pass | 719 |  | Development Team
67 | App crashed after click on Virtual Remote Widget on IR Remote Details Screen . | High | Closed | Pass | 719 | Please refer logs for reference | Development Team
68 | On Explorer remote page , If Remote not support User should get proper error message | Medium | Closed | Pass | 719 |  | Development Team
69 | Click on Plus Button in Dashboard > Select IR Remote> Add Device >Below Error coming 01-02 16:33:33.212 20526-20526/com.panasonic.in.miraie.debug E/OnBoardingAnalytics: com.panasonic.in.miraiecore.utils.MirAIeErrorException: Invalid class name at com.panasonic.in.miraie.onboarding.OnBoardingAnalytics.getScreenName(OnBoardingAnalytics.java:294) at com.panasonic.in.miraie.onboarding.OnBoardingAnalytics.trackScreen(OnBoardingAnalytics.java:93) at com.panasonic.in.miraie.onboarding.OnBoardingInstructionFragment.onResume(OnBoardingInstructionFragment.java:57) | Medium | Closed | Pass | 719 | Please refer logs for reference | Development Team
70 | User in Cool Mode > if User Change FAN Speed from Auto to Low , Mid or High > Change Mode > App keep showing > The command is not available | High | Closed | Pass | 726 |  | Development Team | Fixed
71 | Click on Plus Button in IR Remote Details Page > Go through Explorer Journey>Select AC Brand and Model>Cursor showing on AC Model Search Box > It must need to show in AC Brand Search Box | Low | Closed | Pass | 723 |  | Development Team | Fixed
72 | IR Remote showing Online >User on Details Page > Lock the Phone> Unlock the Phone> User on Details Page> IR Remote showing Offline and it never update to Online untill user back to dashboard and come back details page | High | Closed | Pass | 723 |  | Development Team | Fixed
73 | IR Remote Online > User on Virtual AC Remote Page >Lock and Unlock the phone several times>User are getting error "Please check if your IR remote device is online" Now message getting dismiss but showing 2 times | Low | Closed | Pass | 723 | UI Dismiss | Development Team | Fixed
74 | Please dismiss message "The command is not available" as soon as it shows .. Because if user keep pressing button which command not support . Then message keep persist for longer time | Medium | Closed | Pass | 723 |  | Development Team | NA | With new approach there are very less chances of "Command not supported" toast. Hence this issue is NA with this new approach.
75 | Please show Spiral Waiting for IR Remote Remove Device . In current state after click on Continue user in Setting page but unknown status does it processing remove or not | High | Closed | Pass | 723 |  | Development Team | Fixed
76 | After Offboard IR Remote.. User should land to Dashboard with snackbar message like " IR Remote Device is Removed Successfully" | Medium | Closed | Pass | 723 |  | Development Team | Fixed
77 | We are sending FAN Mode command from IR Remote , After fire command Real AC updated to Dry Mode instead of FAN Mode . This is working fine with Blaze Application | High | Closed | Pass | 726 |  | Blaze Team
78 | Account added with multiple AC Virtual Remotes with different name E.g. Panasonic Remote , Samsung Remote , Off board Main IR Remote with keeping virtual devices on Cloud and Onboard it back . After Onboard Successfully AC Virtual Remotes name change to "IR Remote" | Medium | Closed | Pass | 726 |  | Cloud Team
79 | All AC Controls are failing and Unable to control AC through IR Remote | High | Closed | Pass | 726 |  | Development Team | Fixed
80 | Click on Power ON button of AC Remote , App crashed | High | Closed | Pass | 732 | Please refer logs for reference | Development Team
81 | In some phone like Vivo [Android 12] , Samsung [Android 13] . Below Scenarios failed Click on Rename Remote in AC Remote Page > Edit it> Click on Rename Button>Device is renamed successfully message coming > Click on X button > Keypad not dismiss | Medium | Closed | Pass | 726 |  | Development Team
82 | Offboard Main IR Remote with keeping Child devices on Cloud .. After offboard successfully need to onboard again .. After successfully onboard .. Try to remove Child devices .. Child Device failed to remove | Medium | Closed | Fail | 746 |  | Cloud Team
83 | On Brand and Model Search Page , Click on Right Mark on Keypad .. Keypad should dismiss . Currently it is not dismissing .. User need to press mobile back button or App back button | Medium | Closed | Pass | 732 |  | Development Team
84 | As per precedence logic , We should keep Auto FAN Mode as default for Auto , Dry and FAN AC Mode . If user press Auto FAN Mode then swing getting OFF if in case it Swing in ON condition | High | Closed | Fail | 746 |  | Development Team
85 | IRRemoteExplorer Activity Leaked | High | Closed | Fail | 746 |  | Development Team
86 | App crashed after click on Power ON/OFF Button in Explorer and Save Remote Journey | High | Closed | Fail | 756 |  | Development Team

## TV
Sr No | Issue Description | Priority | Status | Result | AppCenter Version | Remarks | Responsibility | Dev Status | Dev Comments
1 | Save TV Remote shows successful message "AC Remote Saved Successfully" | High | Closed | Pass | 800 |  | Development Team
2 | Except Power ON and OFF TV Other controls like input , Home etc are not working | High | Closed | Pass | 800 |  | Development Team
3 | Sometimes need to press 4 to 5 times .. Even IR device recognized key but not update on TV | High | Closed | Pass | 800 |  | Development Team
4 | If keep mobile phone on standby for sometimes then launch app and send command .. Need to press 4 to 5 times | High | Closed | Pass | 800 |  | Development Team
5 | Enter Key fired with Blank IR code | High | Closed | Pass | 800 |  | Development Team
6 | Please remove "add Model" Text on Title Bar from Brand Selection page for TV and STB. | Medium | Closed | Pass | 800 |  | Development Team
7 | "OK" key is not handled in app yet. only ENTER i can see in app. But in core lib we have OK key. We have to work on this, need to support "OK" in app | High | Closed | Pass | 800 |  | Development Team
8 | Click on Plus Button in Dashboard . App getting Crashed | High | Closed | Pass | 800 |  | Development Team
9 | Onboard device not able to see in Home Dashboard | High | Closed | Pass | 800 |  | Development Team

## STB
Sr No | Issue Description | Priority | Status | Result | AppCenter Version | Remarks | Responsibility | Dev Status | Dev Comments
1 | For TATA Sky , Showing 3 Remotes options. Out of 3 only 1 can able to save | High | Closed | Pass | IR-STB |  | Cloud Team
2 | Saved Remotes most commands are not working . See below table for your reference | High | Closed | Pass | IR-STB |  | Cloud Team
3 | Crashed observe [Scenario – Save Remote > Press on Channel +/-.. Find attached crash log for your reference | High | Closed | Pass | 756 |  | Development Team
4 | IRRemoteExploreActivity has leaked window DecorView@1e0445 Find attached log for your reference | Medium | Closed | Pass | 756 |  | Development Team
5 | For Airtel DTH , Showing 1 Remote option and that too not working | High | Closed | Pass | IR-STB |  | Cloud Team

## IR Learning Bugs+Channel
Sr No | Issue Description | Priority | Status | Result | AppCenter Version | Remarks | Dev Comments | Responsibility
1 | Add Custom Key shows "My IR TV Remote" for AC and STB . It must specific as per category | Medium | Closed | Pass | 783 |  | FIXED | Development Team
2 | Remote image for AC and STB must be as per real image .. Currently for AC custom key , User able to see TV Remote . This might not be correct user experience | High | Closed | Pass | 797 |  | NA/ need discussion | UI/UX Team
3 | For Low resolution phone Add custom keys , number of seconds representation are hide | High | Closed | Pass | 783 |  | FIXED | Development Team
4 | Error message not showing for low resolution if in case user not press remote button | High | Closed | Pass | 783 |  | FIXED | Development Team
5 | For low resolution phone cancel button on Add custom key merge with text "Waiting for the IR device to confirm " | High | Closed | Pass | 783 |  | FIXED | Development Team
6 | For low resolution phone Test custom key button not showing on UI | High | Closed | Pass | 783 |  | FIXED | Development Team
7 | Please make 60 seconds text in Bold | Medium | Closed | Pass | 783 |  | FIXED | Development Team
8 | Make Red and Green LEDs text in Bold Replace tap to Continue with tap to Next as we are showing Next button UI | Medium | Closed | Pass | 783 |  | FIXED | Development Team
9 | Increase the horizontal space between text "Waiting for the IR device to confirm " and Cancel button | Medium | Closed | Pass | 783 |  | FIXED | Development Team
10 | After add custom key on custom key received . As per UI tick mark with circular UI should show but currently we are getting Oval Shape | HIgh | Closed | Pass | 783 |  | FIXED | Development Team
11 | Dialog for save custom key must need shift little above to match final UI design | Medium | Closed | Pass | 783 |  | FIXED | Development Team
12 | Click on Save Key , Saved custom key not able to see in UI . User need to kill and launch application Now added Custom key showing disabled state and User need to back dashbaord then it show in enabled state | High | Closed | Pass | 787 |  | FIXED | Development Team
13 | After save custom key , Keypad must need dismiss | High | Closed | Pass | 783 |  | FIXED | Development Team
14 | App crashed [Add AC Remote > Add one custom key > Remove AC Remote > Add again AC Remote a. First issue Its not removing added custom key for last AC Remote until user not kill app and launch If click on plus button to add another custom key then b. app crashed one time logs above shows | High | Closed | Pass | 783 |  | FIXED | Development Team
15 | App crashed Random [Logs Attached] | High | Closed | Pass | 787 |  | Non reproducible | Development Team
16 | Long press on already created custom key . User able to replace key | Low | Closed | Pass | 783 | This is as per design | NA | Development Team
17 | In UI using number of TV in case of STB. Update it to STB_NUMBERS in STB UI as per updated core lib | High | Closed | Pass | 783 |  | FIXED | Development Team
18 | Volume button working reverse [ For Volume + it works minus volume] | High | Closed | Pass | 787 |  | FIXED | Development Team
19 | Disable UI for not supported capabilities - like Home not available in capability, Red/Blue/Green/Yellow Buttons not available in capability | High | Closed | Pass | 787 |  | FIXED | Development Team
20 | Mute button show number on TV instead of mute STB .. I checked capability we are firing correct IR code as per capability | High | Closed | Pass | 783 |  | NA | Development Team
21 | Onboard device not able to see in Home Dashboard | High | Closed | Pass | 782 |  | FIXED | Development Team
22 | On Dashboard Widget [old Build 778] .. I am able to see Light icons for all categories like AC ,TV and STB . | High | Closed | Pass | 782 |  | FIXED | Development Team
23 | IR remote Details Screen>Click on plus button > Choose TV> Explore Remote> Fire any IR command> After fire successfully on Explorer Page user able to see IR Learning Buttons .. It must not visible on Explorer Journey | High | Closed | Pass | 787 |  |  | Development Team
24 | App crashed 2 times for Saving AC and TV Remote .Log will share on email | HIgh | Closed | Pass | 787 |  |  | Development Team
25 | After add any Remote . a. It is showing in disable state .. User need to go back Dashboard then it update b. it would not update in remote list untill user not go back Dashboard and come back IR remote details screen | High | Closed | Pass | 787 |  |  | Development Team
26 | For STB , We are getting below capabilities but still app shows ON button in Disable state . Tested with Airtel DTH and TATA sky both behave similar Model : ODMIRB_IRB-BLAZE01_STB_67279_140056_0ef555236b53:04 "keyId": "301", "value": "POWER", "irdata": "0000039425;G018EH015BI00A5J0128K0287L01CDM008BN0334$GHIJIKILIKMHIHMHIJIHIKILMNIJIHINIH" }, { "keyId": "302", "value": "POWER OFF", "irdata": "0000039425;G018EH015BI00A5J0128K0287L01CDM008BN0334$GHIJIKILIKMHIHMHIJIHIKILMNIJIHINIH" | High | Closed | Pass | 787 |  |  | Development Team
27 | After add any Custom Key . It is showing in disable state .. User need to go back Dashboard then it update | High | Closed | Pass | 787 |  |  | Development Team
28 | IR Remote showing Online >User on Details Page > Lock the Phone> Unlock the Phone> User on Details Page> IR Remote showing Offline and it never update to Online untill user back to dashboard and come back details page | High | Closed | Pass | 787 |  |  | Development Team
29 | Sequence of devices showing on IR Remote Widget It must be AC , TV and STB . In current implementation it showing like AC , STB and TV | High | Closed | Pass | 783 |  |  | Development Team
30 | OK/ENTER Key handled for TV and STB | High | Closed | Pass | 783 |  |  | Development Team
31 | STB Channel number key not working | High | Closed | Pass | 787 |  |  | Development Team
32 | Onboarding last page shows Spike Guard image | High | Closed | Pass | 787 |  |  | Development Team
33 | IR remote added with Switches & Plugs in any one of Room then it shows in both category like Appliances and Switch & Plugs | High | Closed | Pass | 789 |  |  | Development Team
34 | if the custom key action is currently active on your device message should generic message to user AC - TV /STB TV - AC/STB STB - AC/TV | High | Closed | Pass | 788 |  |  | UX Team
35 | No message after adding STB .. Message should "STB device added successfully" | Low | Closed | Pass | 789 |  |  | Development Team
36 | For ON and OFF Power Keys .. Can we make ON and OFF in Complete Capital Text to align with UI and UX | Low | Closed | Pass | 789 |  |  | Development Team
37 | For tata Sky "capability": "IRB_PlaybackController", Only "value": "REW", "value": "FF", and "value": "STOP", capabilities are available but Bottom sheet shows all capabilities and UI shows in enable state for non-available capabilities | Medium | Closed | Pass | 789 |  |  | Development Team
38 | Custom is adding without pressing any key's from particular remote. | High | Closed | Pass | 790 |  |  | Development Team
39 | For STB and TV remote, ON key is working for both ON and OFF operation. Similarly for OFF key. | High | Open | Fail | 790 |  |  | Firmware Team
40 | if channel response false from API then can we show UI in disable state instead of showing "Something went wrong" message to end user | Medium | Closed | Pass | 800 |  |  | Cloud Team
41 | Select STB Remote>Click on Channel [Ch] >Bottom Sheet will open>Keep cursor on search box > Keypad will open > Bottom sheet must go up and User must able to see proper page for Channels [Currently User need to pull Bottom sheet up to see page correctly] | High | Closed | Pass | 800 |  |  | Development Team
42 | Crashed Observed one time during add AC Remote on click to Save Remote | High | Closed | Pass | 797 |  |  | Development Team
43 | Crashed observed after saving Set Top Box and Click on CH Button | High | Closed | Pass | 797 |  |  | Development Team

## STB Test Report
Remote Functions | TATA Sky | Blaze | Remark
Power ON/OFF | Working | Working
Volume Increase and Decrease | Working | Working
Navigation Up/Down | Working | Working
Navigation Left/Right | Working | Working
Home | Working | Working
Menu/Setting | Working | Working
Help | Working | Working
Guide | Working | Working
Channel Numbers | Working | Working
Enter Button | Working | Working
Play /Pause/Stop | Not Supported for my home Tata Sky Box | Not Supported for my home Tata Sky Box
Mute/Unmute | Working | Working
Back Button | Working | Working
Colour Buttons [Red , Yellow , Blue , Green] | Working | Working
Info | Working | Working

## TV Test Report
Plasma / PA43H4900
Remote Functions | Panasonic | LG | Sony | Haier | BPL | Samsung | Blaze
Power ON/OFF | Working | Working | Working | Working | Not working | Working | Working
Volume Increase and Decrease | Working | Working | Working | Working | Working | Working | Working
Navigation Up/Down | Working | Working | Working | Working | Not working | Not working | Working
Navigation Left/Right | Working | Working | Working | Working | Not working | Not working | Working
Home | Working | Working | Working | Working | Not working | Not working | No button Avaialable
Menu/Setting | Working | Working | Working | Working | Not working | Working | Not Working [No response from TV]
Input | Working | Working | Working | Working | Not working | Working | Working
Sleep Mode | Working | Working | Working | Working | Not working | Working | Not Available
Channel Numbers | Working | Working | Not Working | Not Working | Not working | Not working | Not Tested
Enter Button | Working | Working | Not Supported | Not Supported | Not Supported | Not Supported | Working
Play /Pause/Stop | Working | Working | Working | Working | Not working | Not Supported | Working
Mute/Unmute | Working | Working | Working | Working | Not working | Working but not consistent / Double Tap required | Working
Back Button | Working | Working | Working | Working | Not working | Working | Working
Colour Buttons [Red , Yellow , Blue , Green] | Not Working | Not Working | Not Working | Not Working | Not working | Not working | Not Working
Fast Forward and Fast Reverse | Working | Working | Working | Working | Working | Not Supported | Working
AC | Pansaonic | LG | LG Casssette AC
AC Mode - Auto , Cool , Dry ,Fan , Heat | Working | Working | Working
FAN Speed - Auto , Low , Medium , High | Working | Working | Working
Power ON/OFF | Working | Working | Working
Swing ON/OFF | Working | Working | Working
Temperature Adjustment | Working | Working | Working