## Scenarios
Serial Nu | Test Scenarios | Pass/Fail | Test Comments | Pending Items
1 | >>Bottom Tabs >>Home & Smart Profiles
| User must Click on Smart Profiles bottom tab and must see smart profile details page | Pass
2 | >>Create New Smart Profile
| a. User must click on +button to select device to continue | Pass
| b. User must see rooms details which are available in account | Pass
| c. User must see devices details which are part of in rooms clicking on down arrow button and closing details clicking on Up arrow button | Pass
| d. User must select and deselect devices in rooms | Pass
| e. User must see Continue button enabled state to continue once selected devices in rooms | Pass
| f. User must see below details when clicking on Continue button >Profile Name >Actions >+Add More >Delete icon for each device item >Device details >Create Smart Profile button in disabled status | Pass
| g. Create Smart Profile button should enable once enter profile name | Pass
| h. User must see Profile Created Successfuly bottom toast message when clicking on Create Smart Profile button and navigating back to dash board | Pass
| i. User must see bottom page edit/update device action clicking on right arrow button | Pass
| j. User must update action and close bottom page clicking on x cancel button | Pass
3 | >>View Details
| a. User must see Created profiles on Smart Profile dashboard page including below details on dashboard widget >Profile Name >Number of Devices >Delete icon >Schedule timer option >Play button | Pass
| b. User must click on Scheduled profile widget and must see below details >Actions >Edit button >Devices and their actions details >Schedule timer details with edit icon >Start Now button | Pass | Opening new profile create page
| c. User must click on profile widget with out scheduled >Actions >Edit button >Devices and their actions details >Start Now button >Schedile button | Pass | Opening new profile create page | Start now button is not working
4 | >>Apply Profile
| a. User must applied profile clicking on play button on dashboard widget | Pass
| b. User must see Profile applied successfully toast message | Pass
5 | >>Schedule Profile
| a. User must click on schedule option on profile widget | Pass
| b. User must see schedule bottom popup page with below options and details from profile dashboard >Schedule ON/OFF toggle button >Start Time picker >Repeat days Monday to Sunday (Mon,Tue,Wed,Thu,Fri,Sat,Sun) >Save Button >X option to close bottom popup page | Pass
| c. User must click on profile widget to schedule and navigate to Actions detail page and clicking on schedule button it should allow to schedule from actions details page | Pass | Opening new profile create page
| d. User must see Schedule button in bottom along with Strat now button in actions details page | Pass | Opening new profile create page | Start now button is not working
| e. User must click on schedule button and must see schedule bottom popup page with below options and details >Schedule ON/OFF toggle button >Start Time picker >Repeat days Monday to Sunday (Mon,Tue,Wed,Thu,Fri,Sat,Sun) >Save Button >X option to close bottom popup page | Pass | Opening new profile create page
| f. User must save schedule and must see Scheduled details as Time and days | Pass | Opening new profile create page
| g. User must Edit/Modify schedule clicking on pen icon | Pass | Opening new profile create page
6 | >>Delete Profile
| a. User must delete profile clicking on delete icon from profile widget | Pass
| b. User must see delete popup message with description and Yes/No option | Pass
| c. User must see Profile deleted bottom toast message onces click on Yes button | Pass
7 | >>Edit Profile
| a. User must click on profile widget and must enter to profile details page and see Edit option on the right hand top side | Pass | Edit button is not present
| b. User must click on Edit button and see below details to edit profile >>Profile Name >Actions >+Add More >Delete icon for each device item >Device details >Update Profile button | Pass | Edit button is not present
| c. User must click on +Add More button and must enter to select device details page | Pass | Add button is not present
| d. User must select/Deselect devices in existing profile and click on continue button | Pass | Add button is not present
| e. User must see delete icon for devices and must see delete pop up message to remove device from profile | Pass | Add button is not present
| f. User must see Device removed from the profile toast message after successfully removed | Pass | Add button is not present
| g. User must see updated actions details and must click on update smart profile button in the bottom | Pass | Add button is not present
8 | >>Push Notification
| a. User must receive push notification for Profile applied successfully | Pending
9 | >>Strings localization | Pass

## Bugs Status
Defect Nu | Description | Test Status (Pass/Fail) | Test Comments
1 | App getting crashes clicking on continue button without selecting any devices from rooms. | Pass
2 | App getting crash clicking on create smart profile button without profile name entered. | Pass
3 | Continue button should be disable state only, if user not select any devices from rooms. | Pass
4 | Select a device to continue text info missing | Pass
5 | Create Smart Profile button should enable once enter profile name | Pass
6 | User should navigate to smart profile dashboard details page once successfully created smart profile instead of staying room shown/device selection details page. | Pass
7 | Button Not responding to edit/update device action clicking on right arrow button in create new smart profile page. | Pass
8 | Delete icon is not responding to delete device in create new smart profile page. | Pass
9 | Profile name field accepting all special char and numbers with no limit. | Pass
10 | App getting crashes when user try to select devices from the room for create new profile. (Kids room panel | Pass
11 | App getting crashes when clicking on back button from device selection page for create new profile (One time observed). | Pass
12 | App getting crashes after successfully created smart profile and once navigate back to dashboard. | Pass
13 | App getting crashes while controlling devices from created profile. | Pass
14 | App getting crashes on scrolling up and down on dashboard profile widget. | Pass
15 | App getting crashes deleting on profile from dashboard. | Pass
16 | Delete pop up is coming but not getting delete devices in create new profile page. | Pass
17 | App getting crash when user launching app | Pass
18 | App getting crash when clicking on delete icon from create new smart profile page | Pass
19 | No actions details available after update device actions for create new smart profile page | Pass
20 | Wrong message showing after new schedule and edited schedule successfully | Pass
21 | Wrong message showing after profile updated successfully | Pass
22 | Profile name not getting updated on dashboard widget if user edit/changes profile name and updated successfully | Pass
23 | Start Now button is not working in new profile page, schedule profile page | Pass
24 | No message for Profile deleted bottom toast message once click on Yes button | Pass
25 | No message for Device removed from the profile toast message after successfully removed | Pass
26 | Modes are not getting changing in update action page on create new smart profile/Update profile bottom sheet. (first time it will change one mode to another mode after that will not change, its freeze) | Pass
27 | Do not include Boards/Switches for actions until Sub device is not selected | Pass
28 | Remove Boards/Switches from list if it doesn't have any device | Pass
29 | Remove curtains as device or sub device from device selection list | Pass
30 | Add temperature value on AC bottom sheet | Pass
31 | Show message on screen when there is no profile created | Pass
32 | About delayed in schedule journey takes more than 10 min to triggering, after triggered also takes 10 min time to update actions in application | Pass | API's Issue
33 | Temperature action not getting changed for manual/Scheduled profile applied | Pass | API's Issue
34 | Added time out error message : "Unable to process your request!" – Pass as we agreed with UX team and Ragava | Pass
35 | If you are passing device id is colon separated in create scenes API input data, then we will return the same in get scenes API response. Were you passing the device ID’s as colon separated in the create scenes API input if the devices are having sub devices ? - FIXED (parse error in app code) | Pass | API's Issue
36 | I have updated the smart profile updation and deletion APIs for default scenes acceptance. And updated the Activate scene API for returning the response immediately with 202 status code and run background operation for mqtt control commands. If we try to activate same scene in middle of the background commands, we will return the 409-status code. These fixes are in pre-prod now. Please check and let me know if any issues found | Pass | API's Issue
37 | Fan speed showing 5 -> Updated as discussed | Pass
38 | Fan speed showing 0 -> Updated as discussed | Pass
39 | Supporting plug as individual device for manual scene device selection. Also, added Bottom sheet to update actions for plug | Pass
40 | Fan speed showing 5 :-> It will now show the maximum supported value if more than max range, and it will show minimum supported value if it is less then min range, eg. if it is coming 0 , it will show 1, if it coming 5 it will show 4 because supported values are b/w 1 to 4 | Pass
41 | Add 0 with schedule time, eg. 9 : 2 pm -> 09 : 02 pm | Pass
42 | Disable Brightness widget when toggle off | Pass
43 | Send only rmcps status in case of power off | Pass
44 | 3. Fan Widget disabling on bottom sheet when toggle is off, and disable fan speed widget when not in manual mode like 1 | Pass
45 | Give margin to recycler view on profile list screen | Pass
46 | Hide Smart profiles from home screen dashboard | Pass
47 | Schedule journey is not working | Pass | Cloud issue
49 | Ordering of devices while creating and updating(after creation) Smart profile | Pass
50 | Ordering of capabilities(actions) for devices | Pass

## Transalation Status
Serial No | Page | Scenario | English | Hindi | Pass/Fail | Marathi | Pass/Fail | Tamil | Pass/Fail | Telugu | Pass/Fail | Bengali | Pass/Fail
1 | Select Device | Selecting device | Select a device to continue | जारी रखने के लिए एक डिवाइस चुनें | Pass | सुरू ठेवण्यासाठी डिव्हाइस निवडा | Pass | செலக்ட் அ டிவைஸ் டு கண்டிநூய் | Pass | కొనసాగడానికి పరికరాన్ని ఎంచుకోండి | Pass | চালিয়ে যেতে/কন্টিনিউ করতে একটি ডিভাইস নির্বাচন করুন | Pass
2 | Profile Details Page | Creating a profile | Profile created successfully | प्रोफ़ाइल सफलतापूर्वक बनाई गई | Pass | प्रोफाइल यशस्वीरित्या तयार केले | Pass | ப்ரொவைய்ல் க்ரியேடட் சக்ஸஸ்ஃபுலி | Pass | ప్రొఫైల్ విజయవంతంగా సృష్టించబడింది | Pass | প্রোফাইল সফলভাবে তৈরি করা হয়েছে৷ | Pass
3 | Profile Details Page | updating a profile | Profile updated successfully | प्रोफाइल को सफलतापूर्वक अपडेट किया गया | Pass | प्रोफाइल यशस्वीरित्या अपडेट केले | Pass | ப்ரொவைய்ல் அப்டேடட் சக்ஸஸ்ஃபுலி | Pass | ప్రొఫైల్ విజయవంతంగా అప్ డేట్ చేయబడింది | Pass | প্রোফাইল সফলভাবে আপডেট করা হয়েছে | Pass
4 | Profile List Page | Deleting a profile | Profile deleted | प्रोफ़ाइल मिटा दी गई है | Pass | प्रोफाइल हटवले | Pass | ப்ரொவைய்ல் டெலிட்ட ட் | Pass | ప్రొఫైల్ డిలీట్ చేయబడింది | Pass | প্রোফাইল ডিলিট করা হয়েছে | Pass
5 | Profile Details Page | update profile | Update smart profile | स्मार्ट प्रोफाइल अपडेट करें | Pass | स्मार्ट प्रोफाइल अपडेट करा | Pass | அப்டேடட் ஸ்மார்ட் ப்ரொவைய்ல் | Pass | స్మార్ట్ ప్రొఫైల్ అప్ డేట్ చేయండి | Pass | স্মার্ট প্রোফাইল আপডেট করুন | Pass
6 | Profile Details Page | Edit profile | Edit smart profile | स्मार्ट प्रोफ़ाइल संपादित करें | Pass | स्मार्ट प्रोफाइल संपादित करा | Pass | எடிட் ஸ்மார்ட் ப்ரொவைய்ல் | Pass | ర్ట్ ప్రొఫైల్ సవరించు | Pass | স্মার্ট প্রোফাইল এডিট করুন | Pass
7 | Profile List Page | Profile delete confirmation | Are you sure you want to delete the smart profile? | क्या आप वाकई स्मार्ट प्रोफ़ाइल हटाना चाहते हैं? | Pass | तुम्हाला स्मार्ट प्रोफाइलनक्की हटवायचे आहे का? | Pass | ஆர் யூ ஷோர் வாண்ட் டு டெலிட் த ஸ்மார்ட் ப்ரொவைய்ல் ? | Pass | మీరు కచ్చితంగా డిలీట్ చేయాలని అనుకుంటున్నారా స్మార్ట్ ప్రొఫైల్? | Pass | আপনি কি সত্যিই স্মার্ট প্রোফাইল ডিলিট করতে চান? | Pass
8 | Profile Details Page | Device Remove confirmation | Are you sure you want to remove \n the device from profile? | क्या आप सुनिश्चित हैं कि आप \n डिवाइस को प्रोफ़ाइल से हटाना चाहते हैं? | Pass | तुम्‍हाला खात्री आहे की तुम्‍हाला प्रोफाइलमधून \n डिव्‍हाइस काढायचे आहे? | Pass | ஆர் யூ ஷோர் வாண்ட் டு ரிமூவ் த டிவைஸ் ஃபரம் ப்ரொவைய்ல் ? | Pass | \n పరికరాన్ని ప్రొఫైల్ నుంచి మీరు కచ్చితంగా తొలగించదలిచారా? | Pass | আপনি কি সত্যিই নিজের প্রোফাইল থেকে ডিভাইসটি সরাতে চান? | Pass
9 | Profile Details Page | Applying a profile | Start Now | अभी शुरू करो | Pass | आता सुरू करा | Pass | ஸ்டார்ட் நௌ | Pass | ఇప్పుడే ప్రారంభించు | Pass | এখনই শুরু করুন | Pass
10 | Profile Details Page | Edit option for profile | Edit | संपादन करना | Pass | एडिट | Pass | எடிட் | Pass | సవరించు | Pass | এডিট করুন | Pass
11 | Profile Details Page | Add more device option | Add more | अधिक जोड़ें | Pass | आणखी जोडा | Pass | ஆட் மோர் | Pass | మరిన్ని జోడించు | Pass | আরও যোগ করুন | Pass
12 | Profile List/Details Page | updating a rule/automation | Automation updated successfully | स्वचालन सफलतापूर्वक अपडेट किया गया | Pass | ऑटोमेशन यशस्वीरित्या अपडेट केले | Pass | ஆட்டோமேஷண் அப்டேடட் சக்ஸஸ்ஃபுலி | Pass | ఆటోమేషన్ విజయవంతంగా అప్ డేట్ చేయబడింది | Pass | অটোমেশন/স্বয়ংকৃতভাবে আপডেট সফল হয়েছে | Pass
13 | Profile Details Page | Device removed success message | Device removed from the profile. | डिवाइस को प्रोफ़ाइल से निकाले गये। | Pass | प्रोफाइलमधून डिव्हाइस काढले. | Pass | டிவைஸ் ரிமூவ்ட் ஃபரம் த ப்ரோவைல் | Pass | ప్రొఫైల్ నుండి పరికరం తీసివేయబడింది. | Pass | প্রোফাইল থেকে ডিভাইস সরানো হয়েছে। | Pass
14 | Profile Details Page | Tap text on Empty List page | Tap | त्याप | Pass | टॅप करा | Pass | டேப் | Pass | ట్యాప్ చేయండి | Pass | ট্যাপ করুন/চাপ দিন | Pass
15 | Profile List page | info text on Empty list page | to create a smart profile | एक स्मार्ट प्रोफ़ाइल बनाने के लिए | Pass | एक स्मार्ट प्रोफाइल तयार करण्यासाठी | Pass | டு கிரியேட் அ ஸ்மார்ட் ப்ரொவைய்ல் | Pass | స్మార్ట్ ప్రొఫైల్ సృష్టించడానికి | Pass | একটি স্মার্ট প্রোফাইল তৈরি করতে | Pass
16 | Profile List page | info text on Empty list page | No smart profiles have been created. | कोई स्मार्ट प्रोफ़ाइल नहीं बनाई गई है। | Pass | कोणतीही स्मार्ट प्रोफाइल तयार केलेली नाही. | Pass | நோ ஸ்மார்ட் ப்ரொவைய்ல் ஹவ் பீண் கிரியேட்டட் | Pass | స్మార్ట్ ప్రొఫైల్స్ ఏవీ సృష్టించబడలేదు. | Pass | কোন স্মার্ট প্রোফাইল তৈরি করা হয়নি | Pass
17 | Profile List Page | Not able to apply a profile | Unable to process your request! | आपका अनुरोध संसाधित करने में असमर्थ! | Pass | तुमच्या विनंतीवर प्रक्रिया करण्यात अक्षम! | Pass | அந்ணேபுல் டு ப்ராஸஸ் யூவர் ரெக்வஸ்ட்! | Pass | మీ అభ్యర్థనను ప్రాసెస్ చేయడం సాధ్యం కాదు! | Pass | আপনার অনুরোধ প্রক্রিয়াকরণ/প্রোসেস করতে অক্ষম! | Pass
18 | Device List Page | Info text for smart profile devices | Group your devices & control them all with a single tap or automate them. | अपने उपकरणों को समूहीकृत करें और उन सभी को एक टैप से नियंत्रित करें या उन्हें स्वचालित करें। | Pass | तुमची डिव्‍हाइसेस गटबद्ध करा आणि ते सर्व एका टॅपने नियंत्रित करा किंवा ते ऑटोमेट करा. | Pass | குரூப் யுவர் டிவைஸ் & கன்ட்ரோல் தம் ஆல் வித் அ சிங்கிள் டேப் ஆர் ஆட்டோமேட் தம் | Pass | మీ పరికరాలను సమూహం చేయండి మరియు వాటిని ఒకే ట్యాప్ లేదా ఆటోమేట్ తో నియంత్రించండి. | Pass | আপনার ডিভাইসগুলিকে গোষ্ঠীবদ্ধ করুন এবং একটি একবার ট্যাপ/চাপ দিয়ে সেগুলিকে নিয়ন্ত্রণ করুন বা সেগুলিকে স্বয়ংক্রিয় করুন৷ | Pass
19 | Profile Details Page | button text for create profile | Create new smart profile | नया स्मार्ट प्रोफाइल बनाएं | Pass | नवीन स्मार्ट प्रोफाइल तयार करा | Pass | கிரியேட் நியூ ஸ்மார்ட் ப்ரொவைய்ல் | Pass | కొత్త స్మార్ట్ ప్రొఫైల్ సృష్టించు | Pass | নতুন স্মার্ট প্রোফাইল তৈরি করুন | Pass
20 | Profile Details Page | Profile name info | Profile name | प्रोफ़ाइल नाम | Pass | प्रोफाइल नाव | Pass | ப்ரொவைய்ல் நேம் | Pass | ప్రొఫైల్ పేరు | Pass | প্রোফাইলের নাম | Pass
21 | Profile Details Page | create profile heading | Create smart profile | स्मार्ट प्रोफाइल बनाएं | Pass | स्मार्ट प्रोफाइल तयार करा | Pass | கிரியேட் ஸ்மார்ட் ப்ரொவைய்ல் | Pass | స్మార్ట్ ప్రొఫైల్ సృష్టించు | Pass | স্মার্ট প্রোফাইল তৈরি করুন | Pass
22 | Profile Details Page Bottom Sheet | Action sheet update button text | Update Action | अद्यतन/अपडेट कार्रवाई | Pass | अपडेट क्रिया | Pass | அப்டேடட் ஆக்ஷன் | Pass | చర్యను నవీకరించు | Pass | অ্যাকশন আপডেট করুন | Pass
23 | Profile List page | Creating a new profile | There is no device in home | घर में कोई उपकरण नहीं है | Pass | होममध्ये कोणतेही साधन नाही | Pass | தேர் ஸ் நோ டிவைஸ் இண் ஹோம் | Pass | ఇంటిలో ఎలాంటి పరికరం లేదు | Pass | বাড়িতে কোনো ডিভাইস নেই | Pass
24 | Profile List Page | Applying profile | Profile applied successfully. It may take some time to reflect. | प्रोफ़ाइल सफलतापूर्वक लागू की गई। प्रतिबिंबित होने में कुछ समय लग सकता है। | NA | प्रोफाइल यशस्वीरित्या लागू केले. दिसून येण्यासाठी काही वेळ लागू शकतो. | NA | ப்ரொவைய்ல் அப்டேடட் சக்ஸஸ்ஃபுலி. இட் மே டேக் சம் டைம் டு ரிவ்லெக்ட் | NA | ప్రొఫైల్ విజయవంతంగా అప్లై చేయబడింది. ప్రతిబింబించడానికి కొంత సమయం పట్టవచ్చు. | NA | প্রোফাইল সফলভাবে প্রয়োগ/অ্যাপ্লাই করা হয়েছে৷ এটি প্রদর্শিত হতে কিছু সময় লাগতে পারে। | NA
25 | Profile List Page | Fetching profiles timeout | Unable to process your request! | आपका अनुरोध संसाधित करने में असमर्थ! | Pass | तुमच्या विनंतीवर प्रक्रिया करण्यात अक्षम! | Pass | அந்ணேபுல் டு ப்ராஸஸ் யூவர் ரெக்வஸ்ட்! | Pass | మీ అభ్యర్థనను ప్రాసెస్ చేయడం సాధ్యం కాదు | Pass | আপনার অনুরোধ প্রক্রিয়াকরণ/প্রোসেস করতে অক্ষম! | Pass
26 | Profile List Page | Scheduling a profile | Profile scheduled successfully. It may take some time to reflect. | प्रोफ़ाइल सफलतापूर्वक शेड्यूल की गई. प्रतिबिंबित होने में कुछ समय लग सकता है। | NA | प्रोफाइल यशस्वीरित्या शेड्यूल केले. दिसून येण्यासाठी काही वेळ लागू शकतो. | NA | ப்ரொவைய்ல் செடியுல் சக்ஸஸ்ஃபுலி. இட் மே டேக் சம் டைம் டு ரிவ்லெக்ட் | NA | ప్రొఫైల్ విజయవంతంగా షెడ్యూల్ చేయబడింది. ప్రతిబింబించడానికి కొంత సమయం పట్టవచ్చు. | NA | প্রোফাইল সফলভাবে তালিকাভুক্ত করা হয়েছে৷ এটি প্রদর্শিত হতে কিছু সময় লাগতে পারে। | NA
27 | Schedule bottom sheet | Info for scheduling a profile | A gap of minimum 20 mins from the current time is recommended. | वर्तमान समय से कम से कम 20 मिनट के अंतराल की सिफारिश की जाती है। | NA | सध्याच्या वेळेपासून किमान 20 मिनिटांच्या गॅपची शिफारस केली जाते. | NA | அ கேப் ஆப் மினிமம் 20 மினிட்ஸ் ஃபரம் த கரண்ட் டைம் ஸ் ரெக்கமண்டட் | NA | ప్రస్తుత సమయం నుంచి కనీసం 20 నిమిషాల గ్యాప్ సిఫారసు చేయబడింది. | NA | বর্তমান সময় থেকে ন্যূনতম 20 মিনিট সময় লাগতে পারে। | NA