## iPad
Sr. No | Steps | Issue Description | Priority | Status | Result | Tested Version | Atachements | Remarks | Dev status
1 | Logout > Click on country selection > Observe | App is getting closed/Crash after clicking on country selection during login | High | Close | Pass | 1.3.17(8) |  |  | Development Team
2 | Login > Click on Cart > Observe "OK" button | "OK" button UI Showing 2 different colors | Medium | Close | Pass | 1.3.17(8) |  |  | Done
3 | Login > Click on AC > Observe Fan speed text | Fan speed text is not alligned to icon | Medium | Close | Pass | 1.3.17(8) |  |  | Done
4 | Login > Click on AC > Click on Convert i7 > Observe apply button | Apply button is UI color is not applied completely | Medium | Close | Pass | 1.3.17(8) |  |  | Done
5 | Login> Click on smart profile > Delete profile > Observe | "Yes" button UI color is not applied completely | Medium | Close | Pass | 1.3.17(8) |  |  | Done
6 | Login > Create new smart profile > Observe | Showing 2 different color for "Update action Button" while creating smart profile | Medium | Close | Pass | 1.3.17(8) |  |  | Done
7 | Login > Retrofit controller > Click on assign > Observe Update button | "Update" button in assign devices showing 2 different colors | Medium | Close | Pass | 1.3.17(8) |  |  | Done
8 | Login > Smart profile > create smart profile > Schedule > Edit smart profile > Observe Save button | Showing 2 different color for "Save Button" while editing smart profile | Medium | Close | Pass | 1.3.17(8) |  |  | Done
9 | Login > Smart profile > create smart profile > Select AC > Update action for AC > Observe | Fan speed button and AC modes/temp button is overlaped | High | Close | Pass | 1.3.17(8) |  |  | Done
10 | Login > Refrigerator > Observe | Refrigerator details screen UI broken | High | Close | Pass | 1.3.17(8) |  |  | Done
11 | Login > Refrigerator > Manage Refrigerator > Observe | Not able to scroll above /below in manage refrigerator screen | High | Close | Pass | 1.3.17(8) |  | There's some options like change password and remove device screen etc | not able to reproduce
12 | Login > TLWM > Select any program > Observe > Start wash button | "Start wash" button UI color is not applied completely | Medium | Close | Pass | 1.3.17(8) |  |  | Done
13 | Login > TLWM > Select any program > Start wash > observe | After starting the TLWM program UI is broken completely | High | Close | Pass | 1.3.17(8) |  |  | Done
14 | Login > TLWM > Select any program > Start wash > Auto pause button > Observe Apply button | "Apply" button UI color is not applied completely | Medium | Close | Pass | 1.3.17(8) |  |  | Done
15 | Login > Select Any device > Remove device >Observe Continue button | "Continue" button UI color is not applied completely | Medium | Close | Pass | 1.3.17(8) |  |  | Done
16 | Login > Select Any device > Remove device > Click on add your feedback > Observe continue button | Showing 2 different color for "Continue" button while editing smart profile | Medium | Close | Pass | 1.3.17(8) |  |  | Done
17 | Login > E care > Details > Download doccument > Observe | App is crashing after clicking on download icon in e care doccuments and certificate download from AMC in Miraie dashboard | Medium | Close | Pass | 1.3.17(12)
18 | Login > Dasboard > Observe | all widget should aligned to center | Medium | Close | Pass | 1.3.17(13) |  |  | Center alignment is not as good as left alignment
19 | Login > Dasboard > Observe | Dot need to remove if it is a single devices | Medium | Close | Pass | 1.3.17(13) |  |  | Done
20 | Login > Account > Logout > Observe | Showing 2 different color for "OK" and "Cancel" button while doing logout | Medium | Close | Pass | 1.3.17(13) |  |  | Done
21 | Login > TLWM > Click on timer option > Observe | In scheduled washing, Multiple screens are merged | Medium | Close | Pass | 1.3.17(13) |  |  | Done
22 | Login > TLWM > Wash wizard > Program recommendation > Choose the clothes > select the soil, brightness & load level > Select "No" > Observe | Night wash icon UI is clipped out | Medium | Close | Pass | 1.3.17(13) |  |  | Done
23 | Login > TLWM > Wash wizard > Program recommendation > Choose the clothes > select the soil, brightness & load level > Select "No" > Observe | "Start wash" button UI color is not applied completely | Medium | Close | Pass | 1.3.17(13) |  |  | Done
24 | Login > Click on room > edit room name > Observe | "Update Name" should come in bottom of the screen. | Medium | Close | Pass | 1.3.17(13) |  |  | Development Team Fixed this alignment in all device details screen
25 | Login> AC > Manage Device > observe | "Diagnose device" and "Change Wifi Password" alligned to left. It should aligned to midle | Medium | Close | Pass | 1.3.17(13) |  |  | Done
26 | Login > Smart water Heater > Energy consumption > Observe | "Daily", "Weekly" and "Monthly" are not alligned to tablet screen in Water heater energy consumption | Medium | Close | Pass | 1.3.17(13) |  |  | Done
27 | Login > TLWM > Click on Rinse/Wash minutes / Spin Minutes > observe | "Apply" button UI color is not applied completely | Medium | Close | Pass | 1.3.17(13) |  |  | Development Team
28 | Login > Click on my living room > Observe | VDP details is showing | Medium | Close | Pass | 1.3.19(6) |  | 8826817101 / Pana@8826 | Done
29 | Login > AC > click on "View details" on error > Observe | Refresh icon need to in center alligned | Medium | Close | Pass | 1.3.19(6) |  | 8826817101 / Pana@8826 | Done
30 | Login > AC > click on "View details" on error > Customer care > Observe | "2H23" text should be in red color | low | Close | Pass | 1.3.19(6) |  | 8826817101 / Pana@8826 | Development Team
31 | Login > AC > click on "View details" on error > Customer care > Observe | Marked texts should be in blue color Note: Need to handle this screen from all places in application | low | Close | Pass | 1.3.19(6) |  | 8826817101 / Pana@8826 Need to validate in next build | Already did the color change in error code journey, it will rflect once we merge the branch
32 | Login > AC > click on "View details" on error > Customer care > Observe | "Contact Us" title should come as left aligned with black color text Note: Need to handle this screen from all places in application | Medium | Close | Pass | 1.3.19(6) | Text are showing as Grey color instead of black | 8826817101 / Pana@8826 Need to validate in next build | Already did the color change in error code journey, it will rflect once we merge the branch
33 | Login > AC > Observe error in bottom of the screen | error notification color is shaded | Medium | Close | Pass | 1.3.19(6) |  | 8826817101 / Pana@8826 | Development Team
34 | Login > AC > manage device > Diagnose device > Observe | in diagnose device screen background image is zoomed out | Medium | Close | Pass | 1.3.19(6) |  | 8826817101 / Pana@8826 | Development Team
35 | Login > AC > manage device > Filter health > How to clean > Observe | Showing 2 different color for "Calibrate" button in filter health section | Medium | Close | Pass | 1.3.19(6) |  | 8826817101 / Pana@8826 | Done
36 | login > Anchor fan > Details screen > observe | Power button should be right alligned in anchor fan | Medium | Close | Pass | 1.3.19(6) |  | 8826817101 / Pana@8826 | Done
37 | login > Anchor fan > Details screen > observe | Not able to scroll down in Anchor fan screen | Medium | Close | Pass | 1.3.19(6) |  | 8826817101 / Pana@8826 | Done
38 | Login > AC > Energy consumption > Observe | "Daily", "Weekly" and "Monthly" are not alligned to tablet screen in AC energy consumption | Medium | Close | Pass | 1.3.20(6) |  | 8826817101 / Pana@8826 Need to check for AC, Water Heater, Retrofit 25A switch and TLWM | Development Team
39 | Login > Observe in Dashboard | VDP details is showing in dashboard | Medium | Close | Pass | 1.3.19(6) |  | 8826817101 / Pana@8826 | Development Team

## Lenova Tab
Sr. No | Steps | Issue Description | Priority | Status | Result | Tested Version | Atachements | Remarks | Issues Version
1 | Login > Dashboard > Observe | Dashboard and room widget is not alligned to tablet screen | Medium | Close | Pass | 1.3.30 |  | Dev -> Resolved | Version v1
2 | Login > Click on Room > Observe | If we click on 1st room, 2nd room will open | High | Close | Pass | 1.3.30 |  | Dev -> Resolved | Version v1
3 | Login > Click on "+" icon > Select the product to onboard > set the product for onboarding state > Observe | Keypad is not opening while entering the SSID password during onboarding | High | Close | Pass | 1.3.30 |  | Dev -> Resolved | Version v1
4 | Login > Account > Observe | "Miraie" and "Others" are not alligned to tablet screen | Medium | Close | Pass | 1.3.30 |  |  | Version v1
5 | Login > Account > Change Password > Observe | Keypad is not opening while changing the password Note: Current password and Confirm password section is not working | High | Re-Opened | fail | 350 |  |  | Version v1
6 | Login > AC > Energy consumption | "Daily", "Weekly" and "Monthly" are not alligned to tablet screen in AC energy consumption | Medium | Close | Pass | 1.3.30 |  |  | Version v1
7 | Login > TLWM > Wash Program > Observe | "Default", "Custom" and "Favorite" are not alligned to tablet screen in Wash programs | Medium | Close | Pass | 1.3.30 |  |  | Version v1
8 | Login > Click on switch > Observe | If we click on any widget, it will open next widget | High | Close | Pass | 1.3.30 | "Switches and Plugs" section |  | Version v1
9 | Login > Settings > App tour > Observe | Animation screen is merging with "Connect Devices" | Medium | Close | Pass | 1.3.30 |  | Dev -> New App your journey | Version v2
10 | Login > Water Heater > Energy consumption | "Daily", "Weekly" and "Monthly" are not alligned to tablet screen in water heater energy consumption | Medium | Close | Pass | 1.3.30 |  |  | Version v2
11 | Login > Click on any room > Click back button > Observe | Black screen is observing once user land back to dashboard from room Note : This black screen is coming everywhere inside the application when we come back from any place | Medium | Open | Fail | 323 |  | Part of Optimization build | Version v2
12 | Login > AC > Change wifi password > observe | Once device is not found during onboarding or Change wifi password, it should show the refresh icon surrounded by red circle | Medium | Close | Pass | 323 |  | Dev -> Resolved | Version v2
13 | Login > TLWM > settings > Observe | Consumption details of "Energy" and "Water" not alligned to the screen | Medium | Close | Pass | 323 |  | Dev -> Resolved | Version v2
14 | Login > Ecare > Observe | AMC, Service and Details are not alligned to screen | Medium | Close | Pass | 323 |  | Dev -> Resolved | Version v2
15 | Login > AC > Observe knob of temperature control | AC temperature changing knob color changed Note: Need to change in Miraie dashboard as well | Medium | Open | Fail | 323 |  | Will have to check later as it may take time | Version v2
16 | Login > AC > Settings > Diagnose device > Observe | Background UI screen image is faded. Not able to see clearly | Low | Open | Fail | 323 | Still it is reproducing in new build | Dev -> Resolved | Version v2
17 | Login > AC > Settings > Change WiFi Password > Upadte Device > Observe | Background UI screen image is faded. Not able to see clearly | Low | Open | Fail | 323 | Still it is reproducing in new build | Dev -> Resolved | Version v2
18 | Login > Click on Room > Observe | AC widgets are overlaped with each other when 2 ac is added in same room. | Medium | Open | Fail | 323 |  | Pending , part of v3 | Version v3
19 | Login > Onboard any device > observe after entering the password for wifi | Keypad is not dismissing even after pressing the connect button in WiFi credential page | Medium | Open | Fail | 350 |  |  | Version v3
20 | Login > Dashboard > Observe | Device name is not showing completely | Medium | Open | Fail | 350 |  |  | Version v3
21 | Login > AC > Click on error > View details > Service request > Observe | Grey color Lines and boxes are faded out Note: Need to handle these in Ecare raise service request and adding address screen as well | Low | Open | Fail | 350 |  |  | Version v3
22 | Forgot password journey | Keypad is not opening in "Confirm password" during forgot password journey | High | Open | fail | 350 |  |  | Version v3
23 | Login > Account > Delete account > Observe | Keypad is not opening in password section while deleting the account | High | Open | fail | 350 |  |  | Version v3
24 | Login > Room > Observe device name | Inside room, device name should be as left alligned | Medium | Open | fail | 350 |  |  | Version v3